## Slide 1: Flood Diversion Authority Board Meeting Budget Update and Recommended Contracting Actions Summary
Presented by
Program Management Consultant
April 14, 2016

## Slide 2: FY2016 Program Budget Status [Mar 1, 2016– Mar 31, 2016] (In Thousands)
 | Total Working Budget | Outstanding Encumbrances | Encumbered and Paid FY to Date | Proposed for This Month | Remaining Budget
Land Acquisition | 109,900 | 45,862 | 52,577 |  | 57,323
Construction | 88,000 | 31,964 | 38,419 | 13,252 | 36,330
Design/Permitting | 7,500 | 6,677 | 7,349 |  | 151
Management/ Oversight | 12,900 | 10,861 | 12,344 |  | 556
Other Costs | 17,000 | 510 | 626 |  | 16,374
Mitigation | 800 | - | - |  | 800
Army Corps Local Share | - | - | 2,279 |  | (2,279)
Retention | 1,400 | 366 | 366 |  | 1,034
Total | 237,500 | 96,240 | 113,960 | 13,252 | 110,288

## Slide 3: Recommended Contacting Actions – Management /Oversight
Description | Company | Budget Estimate ($)
Task Order Amendments |  | 
Task Order No. 1, Amendment 3 Material Testing And Abatement Monitoring Adds asbestos abatement monitoring for WP‐42A1.A3 and WP‐43E.2C. Adds asbestos survey and sampling services for WP‐42C.1, WP‐42C.2, WP‐42H.2, WP‐42I.1, WP‐42A1.A3, and WP‐43E.2C. Adds requirements for monthly invoicing and status reporting. | Terracon | 82,500.00
Change Orders |  | 
WP-42A.2 Change Order 6 2nd Street North Pump Station Completion Milestone Changes, Extended Warranty Duration, Modifications to Trash Rack and Rake, and Check Valve Replacement. | IBI | 43,488.99

## Slide 4: Recommended Contacting Actions – Management /Oversight
Description | Company | Budget Estimate ($)
Change Orders |  | 
WP-42C.2 Change Order 1 2nd Street/Downtown – In‐Town Levees, Demolition Administrative schedule delays, removal and cleanup of unknown asbestos containing fire doors, Xcel transformer blow out, spring pavement removal, Xcel Energy and City of Fargo utility expenses, unknown water service disconnect, and unknown asbestos abatement. | Landwehr Construction | 87,263.59
WP-42F.1S Change Order 5 2nd Street North (South of Pump Station) Concrete grading within pump station, unit price change, additional H Pile, bridge abutment seal, traffic signals, and bridge abutment concrete disposal, floodwall connections. | IBI | 68,743.01
Construction Contract Awards |  | 
Recommendation to Award - WP-42F.1N Flood Control, 2nd St N, (North of Pump Station) | IBI | 12,969,699.05